## RICs
ID | Description | Type | Date Identified | Impact | Probability | Importance | Response | Owner | Closure Date
1001 | Minimum experience in Laravel Framework | Risk | 2018-08-20 | 10 | Medium | 5 | Learn from Project Manager | YMT
1002 | Minimum experience in System Analysis | Risk | 2018-08-20 | 10 | High | 6.5 | Learn from Leacture Times | SLWY, HYDNO
1003 | Minimum experience in Project Management | Risk | 2018-08-20 | 30 | Medium | 15 | Learn from Leacture Times | All members
1004 | Difficult to survey the client requirement | Risk | 2018-08-20 | 10 | Medium | 5 | Will discuss supervisor | All members
1005 | getting not much time for project planning within first weeks | Issue | 2018-08-20 | 40 | High | 40 | get extra hours for discussion and planning processes | All members | 2018-08-24
1006 | Online Payment Function | Risk | 2018-08-21 | 50 | High | 32.5 | Will use virtual banking system | All members
1007 | getting not much time for project development within 4 weeks | Risk | 2018-08-22 | 90 | Very High | 72 | Drop less priorities function | All members
1008 | Windows 10 Update Problem | Issue | 2018-08-23 | 20 | High | 20 | Closed windows update and informed to all members | MMK | 2018-08-23
1009 | Cannont access ENU moodle | Issue | 2018-08-23 | 50 | High | 50 | directly learned from p3.express | All members | 2018-08-23